## Sheet1
From | To | Task description
7:25 | 7:35 | Unity WheelCollider documentation
7:35 | 8:00 | Unity WheelCollider tutorial
8:10 | 9:00 | Unity WheelCollider tutorial
9:00 | 9:20 | Dashboard modelling with Probuilder
9:25 | 10:00 | Pedals and gearbox
10:20 | 11:20 | Pedals and gearbox
11:20 | 11:40 | Video
From | To | Task description
11:45 | 12:00 | Trying to figure out the cause of inverted steeringwheel rotation
12:00 | 12:10 | Researching IK
12:10 | ~12:30 | Importing low poly asset pack for character and car visuals.
~12:30 | 13:15 | Modelling missing or unmovable props (steering wheel, handbrake, pedals, gearshift)
13:15 | 13:50 | Importing the new assets, fixing rotation and scale problems. There are some problems with the pedals normals.
13:50 | 13:50 | Realized, that i was editing different files, then what I exported to Unity, cause I made a backup to different folders…
13:50 | 14:10 | Editing the real files… Still, there is some bug with the import, the rotation is off, but it does not really matter.
14:10 | 14:35 | Finished the the car visuals.
14:40 | 16:10 | Importing and stripping down my camera controller from another project. Added different camera positions with limited rotation.
16:10 | 16:15 | Added headlights.
17:00 | 17:20 | Character, tried to create basic sit animation inside Unity.
17:20 | 18:20 | Assigned materials to the car in blender, fixed the import issues.
18:25 | 18:37 | Animating character in Blender.
18:40 | 19:06 | Fixing up bone names in Blender…
19:06 | 19:20 | Character finally proparly imported…
19:40 | 20:10 | Coding AvatarAnimationController (IK)
20:15 | 20:45 | Updating the prefab to the new car.
21:00 | 21:10 | Reseraching Animation layers for the hands.
21:10 | 21:15 | Importing timer from my other project.
21:45 | 21:50 | Researching if there is a buil-in solution, to lerp between lo IK goals. Found that current Ik position can be read, so it can be easilty interpolated forms tart to end.
21:50 | 23:20 | Started to implement it.
0:05 | 2:30 | Finally figured IK interpolation out… :D
2:30 | 4:00 | There are some bugs with the IK interpolation while movin.
11:20 | 11:40 | Solved IK bug.
11:40 | 12:30 | Setting up nicer IK positions.
12:30 | 12:45 | Lerping the rotation sometimes results in the Ik taking the longer rotation. Searching for a fix.
13:11 | 14:35 | Fixing skipping if the goal is changed mid transition.
14:35 | 15:50 | Make it possible to Deatach the ik from the goal, so it will not teleport after the goal, just treat it as a new goal.
17:45 | 18:55 | Ik working correctly for every limb, except the rotation lerp.